## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 100
| Number of testers | 5
| Test cycle duration | 5 days
Status for 08/31/2013
| Number of test cases planned | 20 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 18
| Number of test cases executed overall | 78
| Number of defects encountered today | 2
| Number of defect encountered so far | 10
| Number of critical defects- still open | 3
Overall status
| Number of test cases planned | 100
| Number of test cases executed | 78
| Pass Percentage of the defects | 98%
| Defects density | 2.5 per day
| Critical defects percentage | 20%
©- SoftwareTestingHelp.com

## Regression-1-Detail status(VAL)
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin: View Route | TS_VAL_VIEWROUTES_02 | TC_VAL_VIEWROUTES_02 | Medium | Anjali | 2018-07-21 | PASS
Admin: Logout | TS_VAL_ADMINLOGOUT_01 | TC_VAL_ADMINLOGOUT_01 | Low | Anjali | 2018-07-21 | PASS
User: Book Ticket | TS_VAL_BOOKTKT_01 | TC_VAL_BOOKTKT_01 | Medium | Anjali | 2018-07-21 | Fail | Book_Tickets_01A: Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome, Book_Tickets_25B: The "Check Availabiltiy" button is not working in Chrome and hence rest of the steps in the scenario could not be executed | Major | Open
©- SoftwareTestingHelp.com
| Module names | Test scenario ID | Defect ID Name
| Admin: View Route | TS_VAL_ADDROUTE_01
| Admin: Logout | TS_VAL_ADMINLOGIN_02
| User: Book Ticket | TS_VAL_DELETE_TRAVEL_01 | Book_Tickets_01A Book_Tickets_01B

## Regression-1-Detail status(INV)
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin: Add Route | TS_INV_ADDROUTE_FROM-TO_07 | TC_INV_FROM-TO_07 | Medium | Anjali | 2018-07-21 | Fail | 1)Add_Route_From_To_07A:The "Travels Details" table is Displayed in new window but user is not able to select "Travels Id" | Major | open
| TS_INV_ADDROUTE_FROM-TO_07 | TC_INV_FROM-TO_07 | Medium | Anjali |  | Fail | Add_Route_From_To_07B: The" Bus Details" table is not displayed in new window, hence user is not able to select "Bus Id" | Major | open
| TS_INV_ADDROUTE_FROM-TO_07 | TC_INV_FROM-TO_07 | Medium | Anjali |  | Fail | Add_Route_From_To_07C: Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TS_INV_ADDROUTE_FROM-TO_07 | TC_INV_FROM-TO_07 | Medium | Anjali |  | Fail | Add_Route_From_To_07D:The page is redirected with error Message of "com.mysql.jdbc.MysqlDataTruncation: Data truncation: Incorrect date value: '' for column 'JDate' at row 1 | Major | open
Admin: Add Route | TC_INV_FARE_14 | TC_INV_FARE_14 | Medium | Anjali |  | Fail | 1)Add_Route_Fare_07A:The "Travels Details" table is Displayed in new window but user is not able to select "Travels Id" | Major | open
| TC_INV_FARE_14 | TC_INV_FARE_14 | Medium | Anjali |  | Fail | Add_Route_Fare_07B: The" Bus Details" table is not displayed in new window, hence user is not able to select "Bus Id" | Major | open
| TC_INV_FARE_14 | TC_INV_FARE_14 | Medium | Anjali |  | Fail | Add_Route_Fare_07C: Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TC_INV_FARE_14 | TC_INV_FARE_14 | Medium | Anjali |  | Fail | Add_Route_Fare_07D:The page is redirected with error Message of "java.sql.SQLException: Incorrect integer value: '' for column 'Fare' at row 1" | Major | open
Admin: Logout | TS_INVAL_ADMINLOGIN_03 | TC_INV_ADMINLOGIN_03 | low | Anjali |  | Fail | Adminlog_out_03A:Message is not displayed as text in red color in the top- center of screen, "SORRY! Invalid username/password please try again" Instead of both field takes wrong data and page re-direct to the admin home page | Critical | open
Admin: Add Travel | TS_INV_ADD_TRAVEL_01 | TC_INV_ADD_TRAVEL_01 | Medium | Anjali |  | Fail | Add_Travel_01A:No pop window open with error messaeg for both field | Major | open
| TS_INV_ADD_TRAVEL_01 | TC_INV_ADD_TRAVEL_01 | Medium | Anjali |  | Fail | Add_Travel_01B:Page is redirect with "com.mysql.jdbc.exceptions.MySQLIntegrityConstraintViolationException: Duplicate entry 'T10' for key 'PRIMARY" message when clicking the submit button | Major | open
Admin: View Travel | TS_INV_ADD_BUS_TRAVEL_01 | TC_INV_ADD_BUS_TRAVEL_01 | Low | Anjali |  | Fail | View_Travel_01A:The pop-up window s does not show any error message instead of it shows messages"You are not athorized to access the page" | Major | open
User: Book Tickets | TS_INV_BOOKTKT_05 | TC_INV_BOOKTKT_04 | Medium | Anjali |  | Fail | Book_Ticket_05A:Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TS_INV_BOOKTKT_05 | TC_INV_BOOKTKT_04 | Medium | Anjali |  | Blocked | Book_Ticket_05B:The "Check Availabiltiy" button is not working in Chrome | Critical | open
User: Book Tickets | TS_INV_BOOKTKT_12 | TC_INV_BOOKTKT_07 | Medium | Anjali |  | Fail | BookTicket_12A:Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TS_INV_BOOKTKT_12 | TC_INV_BOOKTKT_07 | Medium | Anjali |  | Blocked | BookTicket_12B:The "Check Availabiltiy" button is not working in Chrome | Critical | open
User: Book Tickets | TS_INV_BOOKTKT_19 | TC_INV_BOOKTKT_10 | Medium | Anjali |  | Fail | Book_Ticket_19A:Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TS_INV_BOOKTKT_19 | TC_INV_BOOKTKT_10 | Medium | Anjali |  | Blocked | Book_Ticket_19B:The "Check Availabiltiy" button is not working in Chrome | Critical | open
User: Book Tickets | TS_INV_BOOKTKT_26 | TC_INV_BOOKTKT_13 | Medium | Anjali |  | Fail | Book_Ticket_26A:Unable to select the date as the pop-up for selecting the date from the calendar is not displayed in Chrome | Major | open
| TS_INV_BOOKTKT_26 | TC_INV_BOOKTKT_13 | Medium | Anjali |  | Blocked | Book_Ticket_26B:The "Check Availabiltiy" button is not working in Chrome
©- SoftwareTestingHelp.com
|  |  |  | Module names | Test scenario ID | Defect ID Name
|  |  |  | Admin: Add Route | TS_INV_ADDROUTE_FROM-TO_07 | Add_Route_From_To_07A Add_Route_From_To_07B Add_Route_From_To_07C Add_Route_From_To_07D
|  |  |  | Admin: Add Route | TC_INV_FARE_14 | Add_Route_Fare_07A Add_Route_Fare_07B Add_Route_Fare_07C Add_Route_Fare_07D
|  |  |  | Admin: Login | TS_INVAL_ADMINLOGIN_03 | Adminlogin_03A
|  |  |  | Admin: Add Travel | TS_INV_ADD_TRAVEL_01 | Add_Travel_01A Add_Travel_01B
|  |  |  | Admin: View Travel | TS_INV_ADD_BUS_TRAVEL_01 | View_Travel_01A
|  |  |  | User: Book Tickets | TS_INV_BOOKTKT_05 | Book_Tickets_052A, Book_Tickets_05B
|  |  |  | User: Book Tickets | TS_INV_BOOKTKT_12 | Book_Tickets_12A, Book_Tickets_12B
|  |  |  | User: Book Tickets | TS_INV_BOOKTKT_19 | Book_Tickets_19A, Book_Tickets_19B
|  |  |  | User: Book Tickets | TS_INV_BOOKTKT_26 | Book_Tickets_26A, Book_Tickets_26B

## Bug report
Defect ID | Test Script ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
Book_Tickets_01A | TS_VAL_BOOKTKT_01 | The Calender Is not displayed in crome browser hence user is not able to select date | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calander icone on the right side of textbox. Expected result: The calender must display in pop-up window in the middle of the page , User must select the future date, The Selected date must appear in textbox beside the calender icone. Actual result: User is not able to select the date of journey as calender does not apper. | Major | Open | Anjali
Book_Tickets_01B | TS_VAL_BOOKTKT_01 | The procedure is not completing due to "Check Availability" button is not working in crome. User does not redirect to next page for further procedure of ticket booking | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button Expected Result: User must redirect to next webpage for further procedure to completed ticket booking process and The Data must store in database after performing the click event of button Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Major | Open | Anjali
Add_Route_From_To_07A | TS_INV_ADDROUTE_FROM-TO_07 | The User is not able to select the Travel Id though the "Travel Details " table appers in pop-up window | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . Expected Result: User must select the Travel Id from the list of Taravel details in pop-up window and the selected value must apper in textbox beside the icone Actual result: The pop-up windows appers with list of travel details but user does not able to select any travel id from the list | High | Open | Anjali
Add_Route_From_To_07B | TS_INV_ADDROUTE_FROM-TO_07 | The" Bus Details" table is not displayed in new window, hence user is not able to select "Bus Id" | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " Expected Result: User must select the Bus Id from the list of Bus details in pop-up window and the selected value must apper in textbox beside the icone Actual result: The pop-up windows does not appers with list of bus details but user does not able to select any bus id from the list | Major | Open | Anjali
Add_Route_From_To_07C | TS_INV_ADDROUTE_FROM-TO_07 | The "Journery date" calender does not apper in pop -up window as user does not able to select the date of journey | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " 6. Enter the Depature Time and Arrival Time 7. Enter the fare of ticket for the added route 8.Select the journey Date from the Calender icon Expected Result: Select the journey Date from the Calender icon on the right side of textbox . The pop-up window is appers with calender and selected date must appers in the textbox besides the icone Actual result: The pop-up calender windows doe not show and user does not able to select the date of journey | Major | Open | Anjali
Add_Route_From_To_07D | TS_INV_ADDROUTE_FROM-TO_07 | The page is redirected with error Message of "com.mysql.jdbc.MysqlDataTruncation: Data truncation: Incorrect date value: '' for column 'JDate' at row 1" | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Select same value "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " 6. Enter the Depature Time and Arrival Time 7. Enter the fare of ticket for the added route 8.Select the journey Date from the Calender icon 9.Click on the Submit button to add the new route Expected Result: User remain on samepage with message "From and To can not be same. Please select different places" data should not store in database Actual result: The user does not get expected message but User redirects to next webpage with message of "com.mysql.jdbc.MysqlDataTruncation: Data truncation: Incorrect date value: '' for column 'JDate' at row 1" | Major | Open | Anjali
Add_Route_Fare_07A | TC_INV_FARE_14 | The User is not able to select the Travel Id though the "Travel Details " table appers in pop-up window | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . Expected Result: User must select the Travel Id from the list of Taravel details in pop-up window and the selected value must apper in textbox beside the icone Actual result: The pop-up windows appers with list of travel details but user does not able to select any travel id from the list | Major | Open | Anjali
Add_Route_Fare_07B | TC_INV_FARE_14 | The" Bus Details" table is not displayed in new window, hence user is not able to select "Bus Id" | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " Expected Result: User must select the Bus Id from the list of Bus details in pop-up window and the selected value must apper in textbox beside the icone Actual result: The pop-up windows does not appers with list of bus details but user does not able to select any bus id from the list | High | Open | Anjali
Add_Route_Fare_07C | TC_INV_FARE_14 | The "Journery date" calender does not apper in pop -up window as user does not able to select the date of journey | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Enter "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " 6. Enter the Depature Time and Arrival Time 7. Enter the fare of ticket for the added route 8.Select the journey Date from the Calender icon Expected Result: Select the journey Date from the Calender icon on the right side of textbox . The pop-up window is appers with calender and selected date must appers in the textbox besides the icone Actual result: The pop-up calender windows doe not show and user does not able to select the date of journey | Major | Open | Anjali
Add_Route_Fare_07D | TC_INV_FARE_14 | The page is redirected with error Message of "com.mysql.jdbc.MysqlDataTruncation: Data truncation: Incorrect date value: '' for column 'JDate' at row 1 '' for column 'Fare' at row 1" | 1. Goto link http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google Crome 2. Select the "Add Route" button 3. Select value "From" field and "To" Field value 4. Click on the "Travel Id" icone on the right side of textbox.The pop-up winddow is display with list of travels details . 5. Click on the "Bus Id" icone on the right side of the textbox . The pop-up window is displaye with list of "Bus Details " 6. Enter the Depature Time and Arrival Time 7. Do not enter the fare of ticket for the added route 8.Select the journey Date from the Calender icon 9.Click on the Submit button to add the new route Expected Result: User remain on samepage with message "Fare is mandatory" data should not store in database Actual result: The user does not get expected message but User redirects to next webpage with message of ""com.mysql.jdbc.MysqlDataTruncation: Data truncation: Incorrect date value: '' for column 'JDate' at row 1 '' for column 'Fare' at row 1" | Critical | Open | Anjali
Adminlogin_03A | TS_INVAL_ADMINLOGIN_03 | admin must get error message while entring wrong user name and password | 1: Goto the link http://ewheelz/ using Google Chrome 2: Click on Admin Login 3: Enter the username into the "Admin ID" field 4: Enter the password into the "Password" field 5: Click "go" button Expected Result: Admin must remain on same page with message of "SORRY! Invalid username/password please try again" Actual Result: Admin does not get any message | Critical | Open | Anjali
Add_Travel_01A | TS_INV_ADD_TRAVEL_01 | Admin must get error message while entring wrong travel Name and Phone Number | 1.Goto http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google crome 2.Select add travel button 3. Enter wrong travel name 4. Select location form the drop-down list 5. Enter the addres 6. Enter wrong phone number and Click Submit button Expect result : Admin get error message in pop -up window "Travel Id" and "Phone Number" is invalid Actual Result : Admin does not get any message which inform admin regarding both field | Major | Open | Anjali
Add_Travel_01B | TS_INV_ADD_TRAVEL_01 | adminis redirect with "com.mysql.jdbc.exceptions.MySQLIntegrityConstraintViolationException: Duplicate entry 'T10' for key 'PRIMARY" message when clicking the submit button | 1.Goto http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google crome 2.Select add travel button 3. Enter wrong travel name 4. Select location form the drop-down list 5. Enter the addres 6. Enter wrong phone number and Click Submit button Expect result : Admin get error message in pop -up window "Travel Id" and "Phone Number" is invalid Actual Result : Admin redirect to next webpage with error mesage " com.mysql.jdbc.exceptions.MySQLIntegrityConstraintViolationException: Duplicate entry 'T10' for key 'PRIMARY" | Major | Open | Anjali
Admin: View Travel | TS_INV_ADD_BUS_TRAVEL_01 | The pop-up windows does not show any error entry message for wronginstead it shows" Bus added successfully" | 1. Goto http://localhost:8080/ewheelz/Validate.jsp?Name=admin&Pwd=admin using Google crome 2. Click on add button on selected trave is form the list displayed 3.A pop-up window is diplayed with with three different field with selected travel id displyed in text box 4. select the bus type form the combo-box list 5.Enter wrong Bus number and click on submit button Expected Result : Admin must get error message "Invalid bus number" in pop-up window. Database must not upadted entered value Acutal Result : Admins gets message of "Bus addes Successfully " | Major | Open | Anjali
Book_Tickets_052A, | TS_INV_BOOKTKT_05 | The Calender Is not displayed in crome browser hence user is not able to select date | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button Expected Result: User must remain on same webpage with pop-up error message "Past date is not allowed.Please select another date." Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Major | Open | Anjali
Book_Tickets_05B | TS_INV_BOOKTKT_05 | The procedure is not completing due to "Check Availability" button is not working in crome. User does not redirect to next page for further procedure of ticket booking | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button Expected Result: User must remain on same webpage with pop-up error message "Past date is not allowed.Please select another date." Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Critical | Open | Anjali
Book_Tickets_12A | TS_INV_BOOKTKT_12 | The Calender Is not displayed in crome browser hence user is not able to select date | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue Expected Result: User must remain on same page with pop-up message "Seat already booked" Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Major | Open | Anjali
Book_Tickets_12B | TS_INV_BOOKTKT_12 | The procedure is not completing due to "Check Availability" button is not working in crome. User does not redirect to next page for further procedure of ticket booking | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue Expected Result: User must remain on same page with pop-up message "Seat already booked" Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Critical | Open | Anjali
Book_Tickets_19A, | TS_INV_BOOKTKT_19 | The Calender Is not displayed in crome browser hence user is not able to select date | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue 11 . Enter customer name,address,phone number,email and gender but leave location than click on continue on redireted page than click continue Expected Result: User must remain on same page with pop-up messesage "Please enter location". Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Major | Open | Anjali
Book_Tickets_19B | TS_INV_BOOKTKT_19 | The procedure is not completing due to "Check Availability" button is not working in crome. User does not redirect to next page for further procedure of ticket booking | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue 11 . Enter customer name,address,phone number,email and gender but leave location than click on continue on redireted page than click continue Expected Result: User must remain on same page with pop-up messesage "Please enter location". Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Critical | Open | Anjali
Book_Tickets_26A, | TS_INV_BOOKTKT_26 | The Calender Is not displayed in crome browser hence user is not able to select date | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue 11 . Enter customer name,address,phone number,email and gender but leave location than click on continue on redireted page than click continue 12.Enter Customer Id,TicketId,PaymentMode,BankName,CardNo and net amount on redirected page than click on continue Expected Result: User must remain on same page with pop-up messesage "Please enter valid card number". Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Major | Open | Anjali
Book_Tickets_26B | TS_INV_BOOKTKT_26 | The procedure is not completing due to "Check Availability" button is not working in crome. User does not redirect to next page for further procedure of ticket booking | 1. Goto link http://localhost:8080/ewheelz/User.html using Google Crome 2. Select the "Book Ticket" button 3. Enter "From" field and "To" Field value 4. Click on the "Jounery date" calender symoble on the rightside of textbox. and select the past journey date 5. Select the type of Bus from the combo-Box list 6.Enter the number of passenger 7. Click on the "Check Avaliability" button 8.Select in radio button to select avalible bus and click on Book now botton 9.Select the boarding ponint on the next redirected web page 10. Select the seat which already have choosen and Click on continue 11 . Enter customer name,address,phone number,email and gender but leave location than click on continue on redireted page than click continue 12.Enter Customer Id,TicketId,PaymentMode,BankName,CardNo and net amount on redirected page than click on continue Expected Result: User must remain on same page with pop-up messesage D24 Actual result: The "Check Availability" button is not working as user does not directed to the next webpage for further process of booking. | Critical | Open | Anjali